## Backup (hidden)
Breaker - Project Planner
Abilities System
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Abilities are hidden and assigned to each part of the Mech | None | TBD | Hold | 10 | 0 | TBD | TBD
Assign Observer to fulfill task of unlocking abilities | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Passive Abilities Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Create Active Abilities Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Create sets of abilities for each Characters | None | TBD | Hold | 50 | 0 | TBD | TBD
Create Ability interaction in game | None | TBD | Hold | 50 | 0 | TBD | TBD
|  |  |  | 160 | 0
Music / Sound / FX
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Define Music Zones | None | TBD | Hold | 10 | 0 | TBD | TBD
Login Screen Background Music | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Attack Sounds - All weapons | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Defense Sounds - All Parts | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Broken Part Sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Character Death Sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
Boss - Special Intro Boss Music | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Warning Sound when first attacked by Player | None | TBD | Hold | 10 | 0 | TBD | TBD
NPC - Interaction with NPCS (Buying or Selling) | None | TBD | Hold | 10 | 0 | TBD | TBD
World - Interactive objects sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
|  |  |  | 100 | 0
Weapons
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create Weapon Class Melee | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class Shotgun | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class SMG | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class Assault Rifle | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class Sniper Rfile | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class Missile Launcher | None | TBD | Hold | 5 |  | TBD | TBD
Create Weapon Class Shield | None | TBD | Hold | 5 |  | TBD | TBD
Create 3 weapons per class | None | TBD | Hold | 50 |  | TBD | TBD
Assign Damage and Rate of Fire to all clases | None | TBD | Hold | 20 |  | TBD | TBD
Define Item Rarity | None | TBD | Hold | 10 |  | TBD | TBD
Assign a Level Requirement for each weapon | None | TBD | Hold | 20 |  | TBD | TBD
Weapons must be equippable | None | TBD | Hold | 20 |  | TBD | TBD
155
Equipment / Character Parts
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create parts of the Mech Characters | None | TBD | Hold | 10 |  | TBD | TBD
Create Chasis Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create Body Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create L Shoulder Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create L Arm Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create L Hand Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create R Shoulder Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create R Arm Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create R Hand Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create Legs Logic | None | TBD | Hold | 10 |  | TBD | TBD
Create Backpack Logic | None | TBD | Hold | 20 |  | TBD | TBD
Create Utilities Logic | None | TBD | Hold | 20 |  | TBD | TBD
140
Skill System
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create a skill for each weapon class | None | TBD | Hold | 50
Create Skill Exp Table | None | TBD | Hold | 20
Create Skill Exp Logic | None | TBD | Hold | 20
Correlate / Weapon Skill with Weapon Damage | None | TBD | Hold | 50
Assign and display set of skills to a character | None | TBD | Hold | 20
160
User Interface (UI)
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Character Info | None | TBD | Hold
Settings | None | TBD | Hold
Inventory | None | TBD | Hold
Server | None | TBD | Hold
Shops | None | TBD | Hold
Garage - Customize | None | TBD | Hold | 50
NPCs Interaction | None | TBD | Hold | 20
0
Combat & Hitpoint System
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create Combat System Logic | None | TBD | Hold | 100
Create Hitpoints System | None | TBD | Hold | 50
Create an attack formula | None | TBD | Hold | 50
Create a defense formula | None | TBD | Hold | 50
Apply attack and defense formulas to Players and NPCs | None | TBD | Hold | 20
The sums of all parts of the player are the total Hitpoints of the player | None | TBD | Hold | 50
320
Character "Must Have" - Checklist
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Character has an HP Bar | None | TBD | Hold | 10
Character name is displayed | None | TBD | Hold | 10
Character is able to receive damage from enemies | None | TBD | Hold | 10
Character is able to deal damage to enemies | None | TBD | Hold | 10
Character is able to chat | None | TBD | Hold | 10
Character is able to interact with NPC or Objects | None | TBD | Hold | 10
Character collide with blocking objects | None | TBD | Hold | 10
Character has an activable User Interface (UI) | None | TBD | Hold | 10
80
Art
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Spritesheet 25 x 25 px | None | TBD | Hold | 10
Character Design - Players | None | TBD | Hold | 10
Character Design - Enemies | None | TBD | Hold | 10
Character Design - NPCs | None | TBD | Hold | 10
User Interface (UI) | None | TBD | Hold | 10
Animations - Combat | None | TBD | Hold | 10
Animations - Characters | None | TBD | Hold | 10
Weapons | None | TBD | Hold | 10
Equipment | None | TBD | Hold | 10
90
World Based
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Grid Based World | None | TBD | Hold | 20 |  | 2018-11-12 | 2018-11-14
Define diferent layers (Ground, Ground Details, Walls, Final Details) | Alfonso Flores | TBD | Hold | 10
Colissions setup for blocking objets such as walls | Alfonso Flores | TBD | Hold | 20
Create different zones such as City and Hunting Areas | Alfonso Flores | TBD | Hold | 100
150
Movement
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Grid Based Movement | None | TBD | Hold | 50 |  | 2018-11-09 | 2018-11-12
Move with Touch/Mouse | None | TBD | Hold | 10
Create a "Speed" Variable assigned to the character | None | TBD | Hold | 20
Assign a correlation value of "Speed" to "Level of the character | None | TBD | Hold | 20
Define a "Speed" value for aplicable NPCS and Enemies | None | TBD | Hold | 10
110

## Project Planner
Breaker - Project Planner
Abilities System | 160
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Abilities are hidden and assigned to each part of the Mech | None | TBD | Hold | 10 | 0 | TBD | TBD
Assign Observer to fulfill task of unlocking abilities | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Passive Abilities Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Create Active Abilities Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Create sets of abilities for each Characters | None | TBD | Hold | 50 | 0 | TBD | TBD
Create Ability interaction in game | None | TBD | Hold | 50 | 0 | TBD | TBD
|  |  |  | 160 | 0
Music / Sound / FX | 100
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Define Music Zones | None | TBD | Hold | 10 | 0 | TBD | TBD
Login Screen Background Music | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Attack Sounds - All weapons | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Defense Sounds - All Parts | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Broken Part Sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Character Death Sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
Boss - Special Intro Boss Music | None | TBD | Hold | 10 | 0 | TBD | TBD
Combat - Warning Sound when first attacked by Player | None | TBD | Hold | 10 | 0 | TBD | TBD
NPC - Interaction with NPCS (Buying or Selling) | None | TBD | Hold | 10 | 0 | TBD | TBD
World - Interactive objects sounds | None | TBD | Hold | 10 | 0 | TBD | TBD
|  |  |  | 100 | 0
Weapons | 155
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create Weapon Class Melee | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class Shotgun | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class SMG | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class Assault Rifle | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class Sniper Rfile | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class Missile Launcher | None | TBD | Hold | 5 | 0 | TBD | TBD
Create Weapon Class Shield | None | TBD | Hold | 5 | 0 | TBD | TBD
Create 3 weapons per class | None | TBD | Hold | 50 | 0 | TBD | TBD
Assign Damage and Rate of Fire to all clases | None | TBD | Hold | 20 | 0 | TBD | TBD
Define Item Rarity | None | TBD | Hold | 10 | 0 | TBD | TBD
Assign a Level Requirement for each weapon | None | TBD | Hold | 20 | 0 | TBD | TBD
Weapons must be equippable | None | TBD | Hold | 20 | 0 | TBD | TBD
155
Equipment / Character Parts | 140
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create parts of the Mech Characters | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Chasis Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Body Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create L Shoulder Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create L Arm Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create L Hand Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create R Shoulder Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create R Arm Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create R Hand Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Legs Logic | None | TBD | Hold | 10 | 0 | TBD | TBD
Create Backpack Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Create Utilities Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
140
Skill System | 160
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create a skill for each weapon class | None | TBD | Hold | 50 | 0 | TBD | TBD
Create Skill Exp Table | None | TBD | Hold | 20 | 0 | TBD | TBD
Create Skill Exp Logic | None | TBD | Hold | 20 | 0 | TBD | TBD
Correlate / Weapon Skill with Weapon Damage | None | TBD | Hold | 50 | 0 | TBD | TBD
Assign and display set of skills to a character | None | TBD | Hold | 20 | 0 | TBD | TBD
160
User Interface (UI) | 170
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Character Info | None | TBD | Hold | 20 | 0 | TBD | TBD
Settings | None | TBD | Hold | 20 | 0 | TBD | TBD
Inventory | None | TBD | Hold | 20 | 0 | TBD | TBD
Server | None | TBD | Hold | 20 | 0 | TBD | TBD
Shops | None | TBD | Hold | 20 | 0 | TBD | TBD
Garage - Customize | None | TBD | Hold | 50 | 0 | TBD | TBD
NPCs Interaction | None | TBD | Hold | 20 | 0 | TBD | TBD
170
Combat & Hitpoint System | 320
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Create Combat System Logic | Hector Jic | TBD | Hold | 100 | 0 | TBD | TBD
Create Hitpoints System | None | TBD | Hold | 50 | 0 | TBD | TBD
Create an attack formula | None | TBD | Hold | 50 | 0 | TBD | TBD
Create a defense formula | None | TBD | Hold | 50 | 0 | TBD | TBD
Apply attack and defense formulas to Players and NPCs | None | TBD | Hold | 20 | 0 | TBD | TBD
The sums of all parts of the player are the total Hitpoints of the player | None | TBD | Hold | 50 | 0 | TBD | TBD
320
Character "Must Have" - Checklist | 80
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Character has an HP Bar | None | TBD | Hold | 10 | 0 | TBD | TBD
Character name is displayed | None | TBD | Hold | 10 | 0 | TBD | TBD
Character is able to receive damage from enemies | None | TBD | Hold | 10 | 0 | TBD | TBD
Character is able to deal damage to enemies | None | TBD | Hold | 10 | 0 | TBD | TBD
Character is able to chat | None | TBD | Hold | 10 | 0 | TBD | TBD
Character is able to interact with NPC or Objects | None | TBD | Hold | 10 | 0 | TBD | TBD
Character collide with blocking objects | None | TBD | Hold | 10 | 0 | TBD | TBD
Character has an activable User Interface (UI) | None | TBD | Hold | 10 | 0 | TBD | TBD
80
Art | 90
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Spritesheet 25 x 25 px | None | TBD | Hold | 10 | 0 | TBD | TBD
Character Design - Players | None | TBD | Hold | 10 | 0 | TBD | TBD
Character Design - Enemies | None | TBD | Hold | 10 | 0 | TBD | TBD
Character Design - NPCs | None | TBD | Hold | 10 | 0 | TBD | TBD
User Interface (UI) | None | TBD | Hold | 10 | 0 | TBD | TBD
Animations - Combat | None | TBD | Hold | 10 | 0 | TBD | TBD
Animations - Characters | None | TBD | Hold | 10 | 0 | TBD | TBD
Weapons | None | TBD | Hold | 10 | 0 | TBD | TBD
Equipment | None | TBD | Hold | 10 | 0 | TBD | TBD
90
World Based | 150
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Grid Based World | None | TBD | Hold | 20 | 0 | TBD | TBD
Define diferent layers (Ground, Ground Details, Walls, Final Details) | Alfonso Flores | TBD | Hold | 10 | 0 | TBD | TBD
Colissions setup for blocking objets such as walls | Alfonso Flores | TBD | Hold | 20 | 0 | TBD | TBD
Create different zones such as City and Hunting Areas | Alfonso Flores | TBD | Hold | 100 | 0 | TBD | TBD
150
Movement | 110
Name | Assigned | Finished Date | Status | Estimation | Hours invested | Timeline - Start | Timeline - End
Grid Based Movement | Chonky | TBD | Hold | 50 | 0 | TBD | TBD
Move with Touch/Mouse | Chonky | TBD | Hold | 10 | 0 | TBD | TBD
Create a "Speed" Variable assigned to the character | Chonky | TBD | Hold | 20 | 0 | TBD | TBD
Assign a correlation value of "Speed" to "Level of the character | Chonky | TBD | Hold | 20 | 0 | TBD | TBD
Define a "Speed" value for aplicable NPCS and Enemies | Chonky | TBD | Hold | 10 | 0 | TBD | TBD
110

## Team Manpower
Estimated | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Miguel Jr | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Hector Jic | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
Luiz Enrike | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
Real | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Miguel Jr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hector Jic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luiz Enrike | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Hours | W1: 1635
Total Weeks | W1: 40
Total Funding | W1: 245250

## Equipment-Parts
Left Shoulder |  |  | Chasis | Right Shoulder
Left Arm |  | Body |  | Right Arm | Backpack | Utilities
Left Hand |  |  |  | Right Hand
Legs

## HitPoints Equipment - Parts
Left Shoulder |  |  | Chasis | Right Shoulder
Left Arm |  | Body |  | Right Arm | Backpack | Utilities
Left Hand |  |  |  | Right Hand
Legs